## Slide 1
Progress Update:
Evaluation Design for a
Knowledge Graph Agent
Work completed, current challenges, and next steps
Kaihao Wang
Master Thesis Progress Meeting
August 2026
1
9 August 2026
Kaihao Wang — KG Agent Progress Update
Notes: Good morning. Today I will report the work I completed during the last two weeks, the current challenges, and my plan for the next two weeks.
The main topic of this period was the evaluation design for a Knowledge Graph Agent. The work is still preliminary. My goal today is to explain the current logic clearly and receive feedback before I implement too much.

## Slide 2
Overall Research Workflow
The evaluation design is validated before the final Agent comparison
1
Research Goal
and Questions
2
Initial Evaluation
Framework
3
Dataset Assessment
and Selection
4
Existing Agent
Analysis
5
Evaluation Prototype
and Unified Logging
6
Pilot with the
Existing Agent
7
Refine Evaluation
Design
8
Improved Agent
Design
9
Validate with the
Improved Agent
10
Comparative Experiments
and Analysis
Current stage:
initial evaluation framework and initial dataset assessment
Throughout the project
Thesis writing and documentation
KG Agent Master Thesis · Progress Update
02
Notes: This slide shows my current idea for the whole thesis workflow.
First, I define the research goal and research questions. Then I design an initial evaluation framework and use it to assess possible datasets. After that, I will analyse the existing Agent in more detail and build an evaluation program together with unified Agent logging.
I then plan to run a pilot test on the existing Agent. This pilot test is mainly used to check whether the datasets, logging format, and evaluation program work together. It is not yet the final performance experiment.
Based on the pilot results, I can refine the evaluation design and improve the Agent architecture. The improved Agent will then be tested with the same evaluation setup. Finally, I will run the formal experiments, analyse the results, and complete the thesis writing.
At the moment, I am mainly working on the evaluation framework and the initial dataset requirements.

## Slide 3
Work Completed in the Last Two Weeks
Dataset review exposed the need for a clearer evaluation structure
1
Initial Review of
KGQA Datasets
Started from available
questions and resources
2
Initial Seven-Layer
Evaluation Framework
Separated capabilities,
tasks, data and metrics
3
Dataset Field
Requirements
Connected evaluation areas
to required annotations
4
Initial Unified Agent
Logging Design
Linked actual execution
to automatic evaluation
ADDITIONAL PROGRESS
Initial reproduction of the first-version Agent
Initial review of KGQA dataset candidates
Current status:
the designs are preliminary and still need practical validation.
KG Agent Master Thesis · Progress Update
03
Notes: At first, I planned to start by reviewing KGQA datasets. However, I found that I could not decide whether a dataset was suitable without first defining what I wanted to evaluate.
For example, different capabilities need different test tasks, metrics, data fields, and Agent records. Therefore, most of my work during these two weeks moved from dataset review to the design of an evaluation framework.
I produced four connected preliminary results: a seven-layer framework, an initial list of required dataset fields, and an initial unified Agent log design.
The key point is that all these results are initial designs. They still need to be tested and revised with the first Agent implementation.

## Slide 4
A Seven-Layer Evaluation Framework
Each layer turns a research question into a concrete evaluation requirement.
1
Capability
Core question
What should the Agent do?
Output: capability definition
2
Test Task
Core question
How can it be tested?
Output: test cases and types
3
Dataset
Requirement
Core question
What data is required?
Output: content and resources
4
Ground Truth /
Annotation
Core question
What is expected?
Output: gold answers and labels
5
Logging
Core question
What should be recorded?
Output: structured run log
6
Metric
Core question
How is it measured?
Output: scores and error types
7
Implementation
Core question
How is it executed?
Output: program and workflow
The framework connects research goals, data, Agent records, metrics, and executable tests.
KG Agent Master Thesis · Progress Update
04
Notes: This is the overall evaluation framework. I divide the design into seven layers so that different concepts are not mixed together.
The first layer is the Agent capability: what should the Agent be able to do? The second layer converts the capability into test tasks. The third layer asks what data and graph resources are required. The fourth layer defines the gold answer or annotation.
The fifth layer defines what the Agent must record during a run. The sixth layer selects the evaluation metrics. The final layer defines how the evaluation is implemented in a program and workflow.
These layers depend on each other. If I add a new test task, I may also need new dataset fields, new log fields, a new metric, and additional implementation work. This is why defining a feasible evaluation scope is currently very important.
Based on this structure, I currently consider four main quantitative evaluation areas. Multi-hop Reasoning, Final Answer, Refusal and Graph Grounding abilities.

## Slide 5
Capability 1: Multi-hop Reasoning
Can the Agent connect several graph facts to answer one question?
Test tasks
Answer questions with 2, 3, and 4+ hops
Compare performance across hop groups
Review selected branching or intersection cases
Evaluation metrics
Answer Accuracy / F1 by hop_count
Optional: Hop Degradation
Selected case analysis
Reasoning quality is observed through answer performance.
Evaluation idea
Group questions by
hop_count
Then compare accuracy or F1
as the number of hops increases.
Required fields
Source
Fields and purpose
Self-built dataset
id · question · gold_answer / answer_set · answer_type · hop_count
hop_count groups the samples; answer_type selects the correct scoring rule.
Existing dataset
question · answer(s) · hop_count
Unified Agent log
sample_id · predicted_answer · answer_status · execution_status
A complete gold reasoning path is not required; selected cases can be reviewed manually.
KG Agent Master Thesis · Progress Update
05
Notes: The first capability is Multi-hop Reasoning. Here, I define it as the ability to connect several facts in the knowledge graph to answer one question.
The main test task is to answer questions with different hop counts, such as two-hop, three-hop, and four-or-more-hop questions. I can then compare the performance of these groups. I may also select a small number of branching or intersection questions for case analysis.
The main metric is answer accuracy or F1 grouped by hop count. Hop Degradation can be an optional metric for comparing how performance changes when the number of hops increases.
For a self-built dataset, the main fields are the question, gold answer, answer type, and hop count. The answer type tells the evaluation program which scoring rule to use. For an existing dataset, I mainly need the question, answers, and hop count. The unified Agent log provides the predicted answer and the execution status.
I do not plan to require a complete natural-language reasoning path for every question. A small number of representative cases can be reviewed manually and used to adjust the analysis method.

## Slide 6
Capability 2: Final Answer
Is the final answer correct, complete, and suitable for the question?
Test tasks
• Answer entity, entity-set, numeric,
Boolean, and date questions
• Detect missing or incorrect answer items
• Review clarity in selected cases
Evaluation metrics
Single answer: Exact Match / Accuracy
Multiple answers: Precision, Recall, F1
Type-specific normalization before scoring
Why answer_type is required
It tells the evaluation program how to
compare the answer. A Boolean answer,
a number, and an entity need different
normalization and scoring rules.
Required fields
Source
Fields and purpose
Self-built dataset
id · question · gold_answer / answer_set · answer_type
optional: acceptable_answers · aliases
Existing dataset
question · answer(s) · answer_type · optional entity_id / aliases
Unified Agent log
sample_id · answer_payload · answer_status · execution_status
Structured answer flow
answer_payload
predicted_answer
final_answer_text
Automatic metrics use the normalized predicted_answer.
KG Agent Master Thesis · Progress Update
06
Notes: The second capability is Final Answer quality. The goal is to check whether the final answer is correct, complete, and suitable for the question.
The evaluation must support different answer types, including a single entity, multiple entities, a number, a Boolean value, or a date. A single answer can use Exact Match or Accuracy. A set of answers needs Precision, Recall, and F1.
The answer type is important because the evaluation program cannot compare every answer in the same way. For example, Boolean values need Boolean normalization, numbers may need numeric comparison, and entities may need identifiers or aliases.
The dataset therefore needs a gold answer or answer set and an answer type. Acceptable answers and aliases are optional fields. In the unified Agent log, the answer payload is converted into a normalized predicted answer. Automatic metrics use this normalized value, while the final answer text is kept for human-readable case analysis.

## Slide 7
Capability 3: Refusal
Can the Agent avoid fabrication when the target KG does not contain an answer?
Test tasks
• Missing entity, relation, or fact
• Questions outside the target KG scope
• Unanswerable question vs. execution failure
• Answerable questions that are wrongly refused
Evaluation metrics
Answerability Accuracy
correct answerable / unanswerable decision
Hallucination Rate
specific answer on an unanswerable sample
False Refusal Rate
incorrect refusal of an answerable sample
Required fields
Source
Fields and purpose
Self-built dataset
id · question · answerable · gold_answer
optional: unanswerable_reason
Existing dataset
question · answer(s) · answerability / no-answer label
Unified Agent log
predicted_answer · answer_status · execution_status · error_type
A correct refusal requires an unanswerable sample and successful execution.
Query or tool failure must not be counted as a correct refusal.
KG Agent Master Thesis · Progress Update
07
Notes: The third capability is Refusal. The main question is whether the Agent can avoid making up an answer when the target knowledge graph does not contain enough information.
The test set should include questions with a missing entity, relation, or fact, as well as questions outside the scope of the target graph. It is also important to distinguish an unanswerable question from a failed execution. For example, a failed tool call is not a correct refusal.
The three initial metrics are Answerability Accuracy, Hallucination Rate, and False Refusal Rate. The first checks whether the Agent correctly decides if a question is answerable. The second measures how often the Agent still gives a specific answer to an unanswerable question. The third measures how often it refuses a question that can actually be answered.
The dataset therefore needs an answerable label. An unanswerable reason is useful but optional. In the Agent log, answer status and execution status must be recorded separately.

## Slide 8
Capability 4: Graph Grounding
Does the answer come from actual KG retrieval rather than model memory or guessing?
Test tasks
• Validate retrieved entities or facts
• Compare the structured answer with
the Agent's actual retrieval results
• Review selected execution traces
Answer–Retrieved Result
Consistency
Can the normalized final answer be
found in or directly supported by the
Agent's recorded KG retrieval results?
Initial common metric
Retrieved Fact Validity Rate
Valid retrieved triples
All recorded retrieved triples
Only calculated when normalized
triples are available.
Required data and logs
Source
Fields or resources
Self-built dataset
id · question · gold_answer · accessible KG / structured triples
conditional: kg_id · kg_version
Existing dataset
question · answer(s) · accessible KG / subgraph · optional query
Unified Agent
log
predicted_answer · retrieved_entities · optional retrieved_facts
Structured answers provide a common final-answer input, but retrieval logs are still required.
Access to the target KG determines how far grounding can be evaluated.
KG Agent Master Thesis · Progress Update
08
Notes: The fourth capability is Graph Grounding. This is the most difficult part of the current framework because a correct answer does not prove that the Agent actually used the knowledge graph.
My first idea is to record what the Agent really retrieved from the graph and compare this with the structured final answer.
The first metric is Answer–Retrieved Result Consistency. It checks whether the normalized answer can be found in, or directly supported by, the recorded retrieval results. This can be used across different Agent architectures if they all record normalized retrieved entities.
The second metric is Retrieved Fact Validity Rate. It checks how many recorded triples really exist in the target graph. However, this metric is only possible when the Agent or its KG tool can provide normalized triples.
The dataset needs access to the target graph or a structured triple resource. The Agent log needs the structured answer and the actual retrieval results.

## Slide 9
Automatic Grounding Metrics Provide Only Partial Evidence
Evaluation question
Answer–Retrieved Result
Consistency
Retrieved Fact
Validity Rate
What can it check?
Whether the answer appears in
the recorded retrieval results
Whether recorded triples exist
in the target KG
Architecture dependence
Requires normalized retrieved
entities or comparable objects
Requires tools that expose or
reconstruct normalized triples
What can it not prove?
The Agent used the correct facts
or reasoning to form the answer
The valid facts were relevant to
the final answer
Answer-type limitation
Numeric or Boolean answers may
not match retrieved entities
Retrieved facts cannot always be
directly compared with the output value
Practical implication
Use lightweight automatic signals where the required records are available.
Add a small number of manual cases for reasoning relevance and difficult answer types.
Guidance needed
How should this be implemented
across different Agents?
KG Agent Master Thesis · Progress Update
09
Capability 4: Graph Grounding
Notes: These two metrics provide useful signals, but they are not complete evidence of Graph Grounding.
Answer–Retrieved Result Consistency can show that an answer entity appeared in the retrieval results. It cannot prove that the Agent used the correct fact or the correct reasoning. Retrieved Fact Validity Rate can show that a recorded triple is valid, but it cannot prove that this triple was relevant to the final answer.
The implementation also depends on the Agent architecture. Some Agents return entities, some return result tables, and some tools may expose graph edges or triples. It is therefore difficult to require exactly the same internal object from every Agent.
There is another problem with answer types. For a numeric or Boolean question, the retrieved entities or facts cannot always be directly compared with the Agent output. For example, a retrieved set of entities may be used to calculate a number, but the final answer is only that number.
My current proposal is to use the automatic signals where the necessary records are available and add a small number of manual cases.

## Slide 10
Capability 5: Problem Understanding (Supporting Case Analysis)
Execution traces help explain errors that final-answer metrics cannot identify.
Test tasks
Select a small number of representative complex questions and inspect their execution traces.
Use the pilot cases to adjust the categories before the formal experiments.
Apply the final categories only for targeted error analysis, not for every dataset sample.
Main purpose
Explain why the Agent failed
and connect errors to later
architecture improvements.
Manual analysis stays lightweight and is calibrated with a small pilot sample.
KG Agent Master Thesis · Progress Update
1
2
3
4
Correct understanding
Goal and constraints retained
Partial understanding
Some conditions are missed
Incorrect understanding
Wrong target, entity, or relation
Execution / tool error
Correct intent, failed execution
10
Notes: I do not currently plan to define a separate main quantitative metric for Problem Understanding.
Instead, I plan to select a small number of representative complex questions and inspect the available execution records.
The analysis can check whether the Agent understood the goal, followed the constraints, selected the correct entities and relations, and produced the expected answer form.
Optional information such as identified entities, selected relations, or subquestions is used only when the Agent already produces it. The purpose is to support the interpretation of the quantitative results.
.

## Slide 11
Core Dataset Field Requirements
The minimum dataset structure needed by the current evaluation framework
Field
Requirement
Purpose
Evaluation areas
Notes
id
Required
Identify each sample
All
Stable and unique
question
Required
Store the full input question
All
Keep all constraints
gold_answer /
answer_set
Required
Provide the expected result
Multi-hop, Final Answer,
Graph Grounding
Single value or set
answer_type
Required
Select the evaluation
method
Final Answer,
Problem Understanding
Entity, set, number, Boolean,
or date
hop_count
Conditional
Group questions by
reasoning hops
Multi-hop
Needed for hop-based
evaluation
answerable
Conditional
Mark whether the KG
contains an answer
Refusal
Both classes are needed
unanswerable_
reason
Optional
Describe why no answer exists
Refusal
Missing entity, missing fact,
or out of scope
11
KG Agent Master Thesis · Progress Update
Notes: This table collects the core dataset fields required by the current design.
Every sample needs an identifier, the complete question, and a gold answer. The answer type is also required because it controls the normalization and comparison method.
Hop count is required when performance is compared across reasoning hops.
For refusal evaluation, the dataset needs an answerable label and should contain both answerable and unanswerable samples. These requirements can define the structure of a supplementary dataset or be used to check whether an existing dataset is suitable.
The next part concerns the information produced during Agent execution.

## Slide 12
Unified Agent Logging: Connects Runs to Evaluation
An initial, architecture-neutral record format for evaluation runs.
What it is
A common structured record of the Agent's final output, execution status, tool calls, and actual KG retrieval results.
Evaluation Dataset
question · gold answer
answer type · test labels
Unified Agent log
structured answer · run status
tool input / result · retrieval records
Produced during each evaluation run
Evaluation program
metrics · error analysis
cross-Agent comparison
Main design decisions
1. Keep the format independent of one Agent architecture or query language.
2. Separate static dataset labels from outputs recorded during an actual run.
3. Add a structured answer node before natural-language answer generation.
4. Record only information that the Agent workflow or its tools actually produce.
Preliminary design:
validate it on the first Agent, then revise it for later Agent versions when needed.
KG Agent Master Thesis · Progress Update
KG Agent
Metrics and
error analysis
12
Notes: By unified Agent logging, I mean a common structured record produced during an agent run. It stores the Agent's structured final answer, execution status, actual tool calls, and KG retrieval results.
This is needed because the dataset only contains questions and standard labels. It does not contain what the Agent actually did. The evaluation program needs both the dataset labels and the run log to calculate metrics and analyse errors.
The first design decision is that the format should not depend on one Agent architecture or one query language. The second is to keep static dataset fields separate from runtime outputs. The third is to add a structured answer node before natural-language generation. The fourth is to record only information that the Agent workflow or its tools already produce.
This logging design is preliminary. I will first test it on the existing Agent. It may need to change after the first pilot or when I develop a later Agent version.

## Slide 13
Complete Unified Agent Log Field Table
Minimum common fields plus conditional and optional records.
Field / type / requirement
Purpose and empty value
sample_id
single · required
Links the run to the dataset sample.
Must not be empty.
answer_payload
single / list · required
Raw structured final answer.
No answer: null; valid empty set: []
predicted_answer
single / list · required
Normalized value for metrics.
No answer: null; valid empty set: []
final_answer_text
single · required
Natural-language user response.
No output: null
answer_status
single · required
answered or unanswerable.
Must not be empty.
execution_status
single · required
success, partial, or failed.
Must not be empty.
Field / type / requirement
Purpose and empty value
tool_calls
list · conditional
Actual tool input, result, and status.
No tool call: []
identified_entities
list · optional
Entities produced by the workflow.
Not recorded: []
selected_relations
list · optional
Relations selected by the workflow.
Not recorded: []
subquestions
list · optional
Explicit subquestions or subtasks.
No decomposition: []
error_type
single · conditional
Main query, tool, or parsing error.
No error: null
answer_status describes whether an answer exists; execution_status describes whether the run worked.
KG Agent Master Thesis · Progress Update
13
Notes: This slide shows the complete initial field list.
The required fields start with sample ID, which connects one run to one dataset question. Answer payload is the raw structured final answer. Predicted answer is the normalized value used by automatic metrics. Final answer text is the natural-language response shown to the user.
Answer status describes whether the Agent answered or judged the question unanswerable. Execution status describes whether the run succeeded, partially succeeded, or failed. These two fields must remain separate. Otherwise, a failed query could be incorrectly treated as a correct refusal.
Tool calls are recorded when tools are actually used. Identified entities, selected relations, and subquestions are optional. They are included only when the Agent workflow produces them. Error type is recorded when a query, tool, or parsing failure occurs.
The empty-value rules are also important. Null means that no value was produced. An empty list can mean that the output is a valid empty set or that an optional list was not recorded, depending on the field definition.

## Slide 14
Structured Answer Node
A structured result is normalized before the final natural-language answer is generated
Structured answer output
Answer normalization
Natural-language generation
Question Understanding · KG Retrieval
Result Integration · Answer Decision
answer_payload
predicted_answer
final_answer_text
Field roles
answer_payload
Original structured result
predicted_answer
Normalized input for automatic evaluation
final_answer_text
Readable answer for the user
Example
{
"answer_payload": ["Agent_B"],
"predicted_answer": ["Agent_B"],
"final_answer_text": "Agent B can communicate with Agent A."
}
KG Agent Master Thesis · Unified Agent Logging
14
Notes: The structured answer is generated after the Agent decides on the answer but before natural-language generation.
The answer payload stores the original structured result, which may be an entity, a list, a number, a Boolean value, or a date.
This result is normalized into the predicted answer, which is used by the evaluation program.
Natural-language generation then produces the final answer text for the user.
This design avoids extracting the answer again from natural-language text and reduces errors caused by wording differences.

## Slide 15
Tool Call Logging Records Actual KG Access
Each tool call maps different Agent interfaces to a small set of common fields.
Field
Requirement
Purpose
tool_name
Required
Name of the query tool, traversal function, or other tool.
input
Required
Structured request sent to the tool, including query or function parameters.
result
Required
Raw content actually returned by the tool.
retrieved_entities
Conditional
Normalized entities extracted from a KG retrieval result.
retrieved_facts
Optional
Normalized triples when the tool can expose or reconstruct them.
success
Required
Whether this specific tool call completed successfully.
error
Conditional
Error message or structured error information when the call fails.
Design decision
input is the request; result is the returned content.
Architecture flexibility
SPARQL · Cypher · graph traversal · custom functions
KG Agent Master Thesis · Progress Update
15
Notes: Tool call logging records how the Agent actually accesses the knowledge graph or another tool.
Each call records the tool name, structured input, raw result, success status, and an error when the call fails. Retrieved entities are recorded when they can be normalized from the result. Retrieved facts are optional and are added only when normalized triples can be exposed or reconstructed.
A key design decision is to keep input and result separate. Input is what the Agent sent to the tool. Result is what the tool actually returned.
Different Agents may use SPARQL, neighbour queries, or custom functions. They can still map their actual input and result to the same common fields.

## Slide 16
Current Challenges
The evaluation design must remain feasible for one master thesis.
CURRENT MAIN CHALLENGE
Defining a feasible evaluation scope
Each evaluation area can become a large research task with many tasks, metrics, fields, and implementation choices.
Other challenge: selecting a dataset strategy
A. Build a new dataset
Advantages
• Full control over fields and labels
• Better fit to the industrial domain
Main cost
KG preparation, question design,
annotation, and validation
B. Combine existing
KGQA datasets
Advantages
• Existing questions, answers, and KGs
• Different capability coverage
Main cost
Inconsistent KGs, schemas, question
styles, and evaluation conditions
C. Use a combined approach
Approach
• Existing datasets for main evaluation
• Small supplementary dataset for gaps
Open point
The additional scope and research value
still need to be defined.
KG Agent Master Thesis · Progress Update
16
Notes: The main challenge is still to define a feasible evaluation scope. Each capability can be divided into many test tasks, metrics, labels, and implementation methods. If I keep all possible ideas, the workload becomes too large for one master thesis.
The second challenge is selecting a dataset strategy.
Option A is to build a new dataset. This provides better control over question types, labels, and the industrial domain, but the cost of graph preparation, question design, annotation, and validation is high.
Option B is to combine existing KGQA datasets. This gives access to existing questions, answers, graphs, and so on. However, different datasets may use different graphs, schemas, question styles, and evaluation conditions.
Option C is a hybrid approach. Existing datasets can support the main evaluation, and a small supplementary dataset can cover missing requirements. The additional scope and research value of this dataset still need to be defined.

## Slide 17
Plan for the Next Two Weeks
First define a feasible scope, then validate the evaluation design in practice.
1
Discuss the scope today
Ask the supervisor to help define
the approximate evaluation scope.
Expected result
A clearer list of core, optional,
and deeper research areas.
2
Refine the framework
Freeze the minimum tasks, fields,
metrics, and logging requirements.
Expected result
A minimum executable
evaluation design.
3
Build the first prototype
Analyse the existing Agent and
implement the first evaluation flow.
Expected result
Initial metric functions and
unified-log integration.
4
OPTIONAL
Run a small pilot
Check whether datasets,
logs, and metrics work
together on the first Agent.
Not guaranteed within
the next two weeks.
Priority:
reduce uncertainty before investing in a larger Agent implementation.
The first pilot validates the evaluation pipeline, not the final Agent performance.
KG Agent Master Thesis · Progress Update
17
Notes: My first priority is to reduce uncertainty before starting a larger implementation.
First, I hope to discuss the evaluation scope with my supervisor today. I would like to identify which areas are core, which are optional, and which need deeper research.
Second, I will refine the evaluation framework and freeze the minimum test tasks, dataset fields, metrics, and logging requirements.
Third, I will analyse the existing Agent in more detail and build the first evaluation-program prototype. This includes initial metric functions and the connection to unified Agent logging.
Fourth, if time permits, I will run a small pilot on the existing Agent. The purpose is to check whether the selected datasets, logs, and metrics work together

## Slide 18
GUIDANCE NEEDED
Questions
for Discussion
The aim is to leave today's
meeting with a clearer and
feasible evaluation direction.
1
Evaluation scope
Which parts should be simplified, removed, optional, or studied in more depth?
2
Graph Grounding
How should it be evaluated across different Agent architectures
and answer types?
3
Unified Agent logging
Do you suggest any changes to the initial unified logging design?
4
Dataset strategy
Should I build a new dataset, combine existing KGQA datasets,
or use a hybrid approach?
Thank you — I would appreciate your guidance.
KG Agent Master Thesis · Progress Update
18
Notes: I would like to finish with four questions for discussion.
First, how should I narrow the evaluation scope? Which parts should be simplified, removed, treated as optional, or studied in more depth?
Second, do you have suggestions for evaluating Graph Grounding across different Agent architectures and different answer types? This is currently the most difficult evaluation area for me to implement.
Third, do you suggest any changes to the initial unified Agent logging design?
Fourth, which dataset strategy is more suitable for this thesis: building a new dataset, combining existing KGQA datasets, or using a hybrid approach?
I hope today's discussion can help me leave with a clearer and feasible evaluation direction. Thank you.